## Sheet1
| EDT | Group meeting | Git clone | Target |  | Business Undestanding / Data Understanding |  | Data Preparation | Data Analysis | Vsualization | Documentation | PPT preparation | Deplpyment
Weekend |  |  |  | Set up repos, load data sets | done
Mon,Oct25 | 9AM
| 10AM |  |  |  |  | Brainstorm business questions. Discusss datasets to answer the questions. | all
11AM
12AM
1PM
2PM
| 3PM |  |  | Submit group contract |  | Discuss each members's responsibilities and communication styles | all
4PM
5PM
6PM
after school
Tue, Oct26 | 9AM
10AM
11AM
12AM
1PM
2PM
3PM
4PM
5PM
| 6PM |  |  |  |  | Discuss findings and recommendations to clients | all
| after school |  |  |  |  | Create storyline | all
Wed, Oct 27 | 9AM
10AM
11AM
12AM
1PM
Group Check-ins | 2PM
3PM
4PM
| 5PM |  |  | Complete notebook, README, images
6PM
after school
Thur, Oct28 | 9AM
10AM
11AM
12AM
Presentation Practice | 1PM
2PM
3PM
4PM
5PM
6PM
after school
Fri, Oct29 | 9AM
10AM
11AM
12AM
Final Presenation | 1PM
2PM
3PM
4PM
| 5PM |  |  | 5PM- Submit link to repo and deliverables